## Community Engagement Plan 2017
Stakeholder Engagement Program Plan
|  | Activities | QTR 1 | QTR2 | QTR3 | QTR4 | Resources required | Responsible Persons | Deliverable | Indicator of Success (short-term) | Indicator of Success (long-term) | M&E Tools | Realated GPP Topic Area | Budget
PLANNING
OBJECTIVE 1: Ensure input from CAB and key community stakeholders in formative activities, including stakeholder identification and design of outreach strategies by Q2
Planning Stage | 1.1 | Conduct landscape analysis with CABs to identify barriers, opportunities for onoing engagement and identifucation of additional community stakeholders | 1 meeting with CAB from each trial site, Mar-April 17 | 0 | 0 | 0 |  | Community Engagement Coordinator to lead | 1 day workshop with research team and CAB; updated contact list, documented feedback | Stakeholder particpation, number and type of stakeholders | Documented feedback and recommendations provided by stakeholders | Stakeholder Analysis Matrix; Form A0 in engageforimpact toolkit | Trial accrual, follow-up, and exit
| 1.2 | Conduct three scoping meetings to assess stakeholders’ level of interest and questions about research:  list stakeholder information | 3 meetings | 0 | 0 | 0 |  | Community Engagement Coordinator to lead | 1 day workshop with documented feedback and recommendations provided by stakeholders | Stakeholder particpation: meeting attendance | Documented feedback and recommendations provided by stakeholders | Form A0 in engageforimpact toolkit | Trial accrual, follow-up, and exit
1.3
1.4
population
OBJECTIVE 2:
Planning Stage | 2.1 | [11 empty] | Staholder advisory mechanisms
| 2.2 | [11 empty] | Staholder advisory mechanisms
2.3
2.4
CONDUCT
OBJECTIVE 3: Strengthen involvement of commnuity stakeholders in protocol review process
Conduct Stage | 3.1 | Meet with CAB to review and refine IC approaches for trial population | Quarterly meeting Mar 17 | 0 | 0 | 0 | Resources for translated protocol summary | Community Engagement and nurse to co-faciltate | Feedback obtained in regular qurterly meeting (March) | Stakeholder participation: meeting attendance and # of recommendations adopted | Number/type of changes incorporated | Meeting template | Informed consent process
| 3.2 | [11 empty] | Informed consent process
3.3
3.4
POST-TRIAL
OBJECTIVE 5:
Post Trial Stage | 5.1 | Evaluate scenarios for trial closure and results dissination: (list stakeholders) | 1 site visit with CAB at each trial site | 1 | 1 | 1 | Resources for CAB meeting | Community Engagement and nurse to co-faciltate | Feedback obtained in meetingmeeting (March) | Stakeholder participation: meeting attendance and # of recommendations adopted | Numbere of groups or organization in community backing results | Meeting template | Trial closure and result dissemination
| 5.2 | [11 empty] | Trial closure and result dissemination
5.3