# STAKEHOLDER ENGAGEMENT STRATEGY

# Engagement Goals and Objectives

The primary goal of the stakeholder engagement program is to:  Increase community awareness (and reduce misconceptions) of HIV/AIDS, clinical research trials, vaginal and rectal microbicides, and PrEP with a focus on reaching most at risk populations.

The primary objectives of the stakeholder engagement program are to:

- Objective 1- Give presentation/ training on PrEP and Microbicides that includes a discussion about research opportunities to community organizations that serve high risk youth (Project Silk, PATF)

- Objective 2- Collaborate with stakeholders that serve at risk populations for community and health events that serve at risk LGBT youth (bring PrEP and research information, present PrEP or research information)

- Objective 3- Attend Youth Advisory Board (YAB) meetings at Project Silk and other youth organizations throughout the trial conduct period to report status of trial and get insight when issues arise (especially regarding communications, media etc)

- Objective 4- Disseminate study results to the YAB and other community organizations.

- Objective 5- Work with the YAB to plan for a community forum to discuss results

# Stakeholder Identification and Analysis

| Stakeholders | Roles How can this stakholder contribute to GPP topic areas for multiple trials ? | Engagement or communciation approach |
| --- | --- | --- |
| List key stakeholders who can contribute to your research (and ideally across multiple trials) | List the GPP topic area or how they contribute to the design, conduct, and analysis of the research | Describe the key mechanism and frequency for each stakeholder |
| MTN/ACTG CAB | Protocol review Stakeholder advisory mechanisms Site selection Informed consent | Monthly meetings |
| AIDS Free Pittsburgh | Formative research activities Disseminating results | Monthly meetings |
| Pittsburgh AIDS Task Force | Stakeholder education plan | Quarterly informal face to face meetings |
| Regional HIV Collaborative | Formative research activities Disseminating results | Meetings every other month |
| Project Silk | Formative research activities Stakeholder advisory mechanisms Stakeholder engagement plan (youth) Stakeholder education plan (youth) Communications plan Trial accrual Disseminating results | Attend YAB meetings every other month |
| Delta Foundation | Stakeholder education plan | Quarterly informal face to face meetings |
| Center for Family Planning Research | Stakeholder engagement plan (women) Stakeholder education plan (women) Trial accrual | Quarterly informal face to face meetings |
| PERSAD | Stakeholder education plan (Trans) Trial accrual | Workshop attendance |
| Masedonia Face | Stakeholder education plan | Face to face meeting |
| Local Colleges and Universities | Stakeholder engagement plan (youth) Stakeholder education plan (youth) | As scheduled |
| Allegheny Health Department | Standard of HIV Prevention Access to HIV Cae and tx Non HIV related care Disseminating results | Face to face meetings |
| Urban League of Pittsburgh | Stakeholder education plan | Face to face meeting |
| YWCA | Stakeholder engagement plan (women) Stakeholder education plan (women) Trial accrual | Quarterly informal face to face meetings |

# M&E

| Trial Stages |  |  |  |
| --- | --- | --- | --- |
|  | Planning | Conduct | Post-trial |
| Impact | Feedback and attendance at stakeholder consultation meeting | Survey to study participants about stigma they face | Feedback from stakeholders ab study via face to face interviews Feedback from stakeholders ab study via meeting |
| Metrics for Each Trial Stages | Attendance at PreP workshops Feedback from PrEP workshops |  | Attendance at community forums to disseminate results |

# GPP Workplan

Objective 1- Give presentation/ training on PrEP and Microbicides that includes a discussion about research opportunities to community organizations that serve high risk youth

(Completed by Community Educator.  Cost- marginal)

| Stakeholder | Timeline | Deliverable | GPP area | Indicator of success |
| --- | --- | --- | --- | --- |
| Project silk | Q3 2016-Q4 2017 | Score 8-10 on survey | Stakeholder Education plan | Complete survey after presentation |
| PERSAD | Q3 2016-Q4 2017 | Score 8-10 on survey | Stakeholder Education plan | Complete survey after presentation |
| YWCA | Q3 2016-Q4 2017 | Score 8-10 on survey | Stakeholder Education plan | Complete survey after presentation |
| Local universities | Q3 2016-Q4 2017 | Score 8-10 on survey | Stakeholder Education plan | Complete survey after presentation |

Objective 2- Collaborate with stakeholders that serve at risk populations for community and health events that serve at risk LGBT youth (bring PrEP and research information, present PrEP or research information)

Completed by Community Educator.  Cost $250-$500 per event (registration, give aways, educational materials)

| Stakeholder | Timeline | Deliverable | GPP area | Indicator of success |
| --- | --- | --- | --- | --- |
| AIDS Free Pittsburgh | Q3 2016-Q4 2017 | - Number of registry sign ups - Number of educational materials distributed to community | - Stakeholder Education plan - Trial accrual | - Any new youth registry participants - Distribution of educational materials relative to attendance of event |
| Pittsburgh AIDS Task Force | Q3 2016-Q4 2017 | - Number of registry sign ups - Number of educational materials distributed to community | - Stakeholder Education plan - Trial accrual | - Any new youth registry participants - Distribution of educational materials relative to attendance of event |
| Delta Foundation | Q3 2016-Q4 2017 | - Number of registry sign ups - Number of educational materials distributed to community | - Stakeholder Education plan - Trial accrual | - Any new youth registry participants - Distribution of educational materials relative to attendance of event |
| PERSAD | Q3 2016-Q4 2017 | - Number of registry sign ups - Number of educational materials distributed to community | - Stakeholder Education plan - Trial accrual | - Any new youth registry participants - Distribution of educational materials relative to attendance of event |
| Project Silk | Q3 2016-Q4 2017 | - Number of registry sign ups - Number of educational materials distributed to community | - Stakeholder Education plan - Trial accrual | - Any new youth registry participants - Distribution of educational materials relative to attendance of event |
| Urban League | Q3 2016-Q4 2017 | - Number of registry sign ups - Number of educational materials distributed to community | - Stakeholder Education plan - Trial accrual | - Any new youth registry participants - Distribution of educational materials relative to attendance of event |
| YWCA | Q3 2016-Q4 2017 | - Number of registry sign ups - Number of educational materials distributed to community | - Stakeholder Education plan - Trial accrual | - Any new youth registry participants - Distribution of educational materials relative to attendance of event |

Objective 3- Attend Youth Advisory Board (YAB) meetings at Project Silk and other youth organizations throughout the trial conduct period to report status of trial and get insight when issues arise (especially regarding communications, media etc)

Completed by Community Educator.  Cost marginal (reimbursement for travel)

| Stakeholder | Timeline | Deliverable | GPP area | Indicator of success |
| --- | --- | --- | --- | --- |
| Project Silk | Q1 2017-Q4 2017 | Verbal and written report | Trial accrual and follow up | Attendance at meetings |

Objective 4- Disseminate study results to the YAB and other community organizations.

Completed by community educator.  Cost marginal

| Stakeholder | Timeline | Deliverable | GPP area | Indicator of success |
| --- | --- | --- | --- | --- |
| Project Silk | Q1 2018- Q4 2018 | Verbal and written report | Trial accrual and follow up | Attendance at meetings |
| AIDS Free Pittsburgh | Q1 2018- Q4 2018 | Verbal and written report | Trial accrual and follow up | Attendance at meetings |
| HIV collaborative | Q1 2018- Q4 2018 | Verbal and written report | Trial accrual and follow up | Attendance at meetings |
| Pittsburgh AIDS Task Force | Q1 2018- Q4 2018 | Verbal and written report | Trial accrual and follow up | Attendance at meetings |
| PERSAD | Q1 2018- Q4 2018 | Verbal and written report | Trial accrual and follow up | Attendance at meetings |
| YWCA | Q1 2018- Q4 2018 | Verbal and written report | Trial accrual and follow up | Attendance at meetings |

Objective 5- Work with the YAB to plan for a community forum to discuss results

Completed by community educator.  Cost $500-$1000 for venue and food

| Stakeholder | Timeline | Deliverable | GPP area | Indicator of success |
| --- | --- | --- | --- | --- |
| Project Silk | Q1 2018- Q4 2018 | Community Forum | Trial exit Disseminating results | Attendance at Forum is >50 and included youth |